ITEM NO. 04 (B-41)

- Name of work- Establishing 33KV Electric Sub-Station at SANJAY CAMP Chanakya Puri.

- Name of the Department- ELECTRICITY DEPARTMENT

- Brief history of the proposals- A number of new embassies are coming up in the nearby area. The load of the existing embassies is also increasing day by day. As such it has been proposed to construct a 33KV Sub-station in the area to meet the growing load demand. The 66KV S/Stns are also to be established at Bapu Dham and State Guest House. This S/S will utilize the power available at these two sub-stations. Therefore, two nos. 33/11KV, 16/20MVA transformers have been proposed at this S/S.

The land for construction of 33KV  Sub-station has already been allotted to NDMC by L&DO. The building plans have been finalized and drawings issued to Civil Engg. Department. The scheme is a part of XIth five year plan which has been technically cleared by CEA vide No. DPD/UT/312(NDMC)/2007/436 dtd. 26.06.07

4.	Detailed proposal on the Project-

To meet the load demand  following have been  proposed in the estimate.

(i)		16/20MVA, 33/11KV Pr. Transformer – 2 Nos.

(ii)	33KV, 1250 A, 1500 MVA, SBB  Indoor Type GIS 7 Panel   Board – 1 No.

(iii)	11KV,  1250 A, 350 MVA, SBB Indoor Type SF-6/VCB 13 Panel Board- 2 Nos.

(iv)	The S/S is proposed to be fed through 33KV, 3x400 Sq.mm XLPE Cable from 66KV S/S  State Guest House   and 66KV S/S Bapu Dham.

The cost of the above equipments comes out to Rs. 1192.27 Lacs.

The cost of the construction of building, as intimated by Civil Engineering Deptt., is Rs. 142.50 Lacs.

Total estimated cost of the Project comes out to Rs. 1334.77 Lacs including 3% contingencies. The scheme has now been outsourced to M/s Power Grid Corporation of India Limited for turnkey executions of 33 KV ESS.

5.	Financial Implications- The estimated cost for establishing 33KV S/S at SANJAY CAMP Chanakya Puri is Rs. 1334.77 lacs chargeable to the head of a/c E.4.1.

- Implementation schedule with timeliness for each stage including internal processing: - The scheme has been outsourced to M/s Power Grid Corporation of India Limited for turnkey execution and as per MOU completion time is 24-30 months.

7.	Comments of the Finance Department on the subject-

The finance deptt. has concurred in the preliminary estimate amounting to Rs. 1334.77 lacs subject to-

- Approval of the competent authority.

- Availability of funds.

- Certification by the department that the work would be got executed after adhering the codal provisions.

- Department has not afforded satisfactory reply as to whether proposed 66 KV Sub-station Bapu Dham and State Guest House from which power to sub-station Sanjay Camp Chanakya Puri would be made available; would be completed and commissioned in time. Our concurrence is further subject to certification that sub-station Bapu Dham and State Guest House would be commissioned in time to feed sub-station Sanjay Gandhi Camp Chanakya Puri

- Comments of the Department on comments of Finance Deptt:

Observation of Finance Deptt. are clarified as under:-

1. 		Approval of the competent authority being sought.

2.    Rs. 5 Lacs has been kept for this work in the RE 2007-08  and suitable provision will be kept in the subsequent years.

3.    The work has been out-sourced to the PGCIL for turnkey execution

4.	The 66 KV ESS at Bapu Dham and state Guest House have also been outsourced to M/s Power Grid Corporation of India limited for Turnkey execution. As per time scheduled given by M/s PGCIL ,the completion of work will be within 24-30 months, However, these two schemes are also related with upgradation of Ridge valley ESS to 220 KV level by M/s Delhi Transco Limited. DTL has proposed to upgradation the same by 2010

- Legal implications of the Project: - No legal implication is involved.

10.	Details of Previous Council Resolution- Nil

11.	 Comments of the Law Deptt. on the Project:

No legal point is involved.  This has our concurrence.

12.   Comments of the deptt. on the Law Deptt.      Nil

13.  Recommendation- The case is noted to the Council for sanction of the estimate amounting to Rs. 1334.77 lacs and also be accord administrative approval and expenditure sanction for the estimated amount for establishing 33KV ESS at SANJAY CAMP Chanakya Puri.  The work has been out-sourced to M/s PGCIL for turnkey execution of the work.

14.   Draft Resolution- Resolved by the Council that the estimate amounting to Rs.1334.77 lacs is sanctioned and A/A & E/S accorded for the estimate amount for establishing 33KV Electric Sub-Station at SANJAY CAMP Chanakya Puri. The work has been out-sourced to M/s PGCIL for turnkey execution of the work.

COUNCIL’S DECISION

Resolved by the Council to accord administrative approval and expenditure sanction to the estimate amounting to Rs.1334.77 lacs for establishing 33 KV Electric Sub-station at Sanjay Camp, Chanakya Puri, New Delhi.  The work has been outsourced to M/s PGCIL for turnkey execution of the work.

Further resolved by the Council that the approval of the Council was subject to the condition that Chief Engr. (Elect.) shall certify that the works for execution of 66 KV Electric Sub-station at Bapu Dham and State Guest House, also outsourced to M/s POWERGRID, will be completed simultaneously along with 33 KV Electric Sub-station at Sanjay Camp within 24 – 30 months as per time schedule given by M/s POWERGRID.