# ITEM NO. 28 (B-20)

1. 	Name of the Project:- Providing 66KV cable from S/S Park street to S/S State Guest House

2. 	Name of the Department Concerned:-    Electricity Department

3. 	Brief history of the project:-

The scheme for establishing 66KV S/S at State Guest House with 1x50MVA, 66/33KV transformer and 1x20MVA, 66/11KV transformer has been approved by CEA as part of VIIIth Plan Works vide letter No. DPED/312(DEL)/97 dated 5.8.97

One no. 66KV, 630 sqmm. feeder was laid, which is presently energized on 33KV level and shall be shifted/terminated on 66KV bay after completion of the upgradation work of S/S Ridge Valley to 220KV level.

NDMC constituted a Committee to prepare a road map for revamp of electrical system in NDMC, under the over all guidance and convenership of Sh. Y.P. Singh, Chairman ECGRE. The Committee proposed to lay the second 66KV feeder from 220KV S/S Ridge Valley of DTL to 66KV ESS Bapu Dham and State Guest House of NDMC to make full utilization of the installed capacity. The estimate for the scheme was prepared by the Committee and submitted to the Deptt. However, the said estimate could not be processed due to non availability of additional 66KV bays at 220KV S/S Ridge Valley of DTL.

Keeping in view the above constraints, a meeting was held in the chamber of Advisor (Power) on dated 2.3.09 wherein Advisor (Elect.), CE (E-II) and other senior officers of NDMC were present and minutes of meeting were circulated vide No. EE(E)C-VI/D-1277 dated 26.03.09.

It was deliberated and decided in the meeting that due to non availability of 66KV bays at S/S Ridge Valley, in place of 66KV feeder from S/S Ridge Valley to S/S State Guest House, 66KV 1000sqmm./single Core cable will be laid from S/S Park Street to S/S State Guest House, since a 66KV bay is available at S/S Park Street.

4. 	Detailed proposal on the Project: -

Following has been proposed in the estimate:

1.	66KV, stranded Al. Conductor XLPE cable Single core of size 1000sq.mm (Feeder length 7.5 Km) is proposed to be laid from S/S Park Street to S/S State Guest House to match the transforming capacity.

2.	145/66KV, 3150A, 40KA, GIS Panels (one for termination of the proposed feeder and other as spare for future use)   - 2 Nos.

5. 		Financial implications of the proposed project:-

The estimated cost for laying of 66KV feeder from S/S Park Street to S/S State Guest House is Rs.1806.69 Lacs including 3% contingencies, chargeable to the head of A/c E-4.1.

6.	Implementation schedule with timeliness for each stage including internal processing:-

The scheme for laying of 66KV feeder from S/S Ridge Valley to S/S State Guest House has been outsourced to M/s Power Grid Corporation of India Limited for turnkey execution to be completed by June,2010. Now instead of this work, M/s PGCIL shall execute the work of providing 66KV, 1000sqmm./SC cable from S/S Park Street to S/S State Guest House.

- Comments of the Finance Deptt. on the subject:-

Finance have seen the case vide Diary No. 2049/Finance/R Elect. Dated 11.09.09 & concurred with no comment.

8.	Comment of the Deptt. on comments of Finance Deptt.:-

No comments.

9.	Legal implication of the Project: -

No legal implication is involved.

- Details of previous Council resolution:- 	NIL

11.	Comments of the Law Deptt. on the project:- 	NIL

12. 	Comments of the Deptt. on the comments of Law Deptt.:-    NIL

13. 	Certificate on CVC guidelines: -

All CVC guidelines shall be adhered to while processing the case.

14. 	Recommendation of the Deptt. : -

The estimate amounting to Rs.1806.69 Lacs including 3% contingencies for “Providing 66KV cable from S/S Park Street to S/S State Guest House” may be placed before the Council to approve the change in scheme, accord administrative approval and expenditure sanction. Since the work is of urgent nature approval may be accorded to get the work executed through M/s PGCIL. Further, approval is also solicited to take further action in anticipation to confirmation of the Minutes of Council Meeting.

15. 	Draft Resolution: -

Resolved by the Council that change in scheme, administrative approval & expenditure sanction is granted to the estimate amounting to Rs. 1806.69 Lacs for “Providing 66KV cable from S/S Park Street to S/S State Guest House” and to get the work executed through M/s PGCIL. Further approval is accorded to take action in anticipation to confirmation of the Minutes of Council Meeting.

COUNCIL’S DECISION

Resolved by the Council to accord approval for change in the scheme and also to accord administrative approval & expenditure sanction to the estimate amounting to Rs.1806.69 Lacs for “Providing 66KV cable from S/S Park Street to S/S State Guest House” and to get the work executed through M/s PGCIL.

It was also resolved that further action in the matter be taken in anticipation of confirmation of the minutes by the Council.

1. 	Name of the subject/Project:-

Construction of Multipurpose Gymnasium at Laxmi Bai Nagar New  Delhi. including

electrical works ( composite work ).

2. 	Name of Department :- Civil Engineering Department Zone-II.

3. 	Brief History of the Subject:-

Establishment and maintenance of gymnasium  is one of the function of the council. There is a demand from  the several quarter of the society living in Laxmi Bai Nagar and adjoining area for the construction of multipurpose Gymnasium and social welfare hall at Laxmi Bai  Nagar. Resident Welfare Association of Laxmi Bai Nagar has also been desiring for the construction of Multipurpose Gymnasium at Laxmi Bai Nagar area as there is no such facilities  available in this locality. Considering the above demand, it has been decided to  construct Gymnasium and other facilities at Laxmi Bai Nagar adjacent to working Girl’s Hostel Laxmi Bai Nagar.

4. 	Detailed proposal on the subject/Project:

A/A and E/S for Rs. 5,00,72,200/- was accorded vide Reso No. 05(A-130)                    dt. 26.02.2009 . After getting the detailed estimate technically sanctioned and draft NIT approved . Item rate tenders for the above work were  invited.

In response to the above, three tenders were received on 17.8.09 through e-tendering . Details are as under :-

Estimated cost put to tender :- Rs. 2,70,64,110/-

| Sl.No. | Agency | % quoted | Amount | Remarks |
| --- | --- | --- | --- | --- |
| 1. | M/s Bhasin Construction | 9.62% above | 2,96,68,988/- | L-1 |
| 2. | Vir Bhan Mittal | 15.33% above | 3,12,67,703/- | L-2 |
| 3 | M/s India Guniting Corpn. | 26.89% above | 3,43,42,688/- | L-3 |

The justification duly checked by planning works out to 11.48% above the estimated cost of Rs. 2,70,64,110/-, against which the lowest rate quoted by the  lowest  tenderer  is  9.62% above the estimated cost overall percentage of tendered cost work  out to 1.66%  below  the  justified  cost of tender. The case was duly recommended by planning for acceptance  and was sent to Finance for their concurrence. The Finance have concurred the case vide their diary No.2101-/Finace dated  15.9.09

5. 	Financial implications of the proposed project/Subject.

The total financial implication for the above work is Rs. 2,96,68,988/-

6.  	Implementation Schedule

Time of complication of work:         15 Months after the  award of work.

7. 	Comments of the Finance Deptt. on the subject.

In view  of  checklist  position , we  concur in  the recommendation of CE(C-II)  for award  of work  to L-I , M/s  Bhasin Const.  Co.  at their  tendered rates  amounting  to  Rs.2,96,68,988/-  (Rupees  two  core  ninety six  lakh  sixty  eight  thousand nine  hundred eighty  eight  only)i.e.  9.62%  above the  EC of  Rs. 2,70,64,110/-  and against justified  rates of  11.48%  above EC

8. 	Comments of the  department on comments of finance Department.

No comments in view of concurrence of Finance.

Finance department has seen and there are no comments to offer.

9. 	Legal implication of the project.

Nil.

10.   	Details of previous Council resolutions, existing law of Parliaments and Assembly on the Subject.

- Reso. No. 05(A-130) dt. 26.2.09 .

11. 	Comments of the Law Department on this project.

No law point.

12. 	Comments of the Department on the comments of Law Departments.

Nil.

13. 	Certification  by the department that all  Central Vigilance Commission (CVC) guidelines have been  followed while processing the case.

Certified that all  Central Vigilance Commission ( CVC) guidelines have been  followed while processing the case.

14. 	Recommendation:-

The case  is placed before the Council for award of work to M/s Bhasin Construction  at their tendered amount of  Rs. 2,96,68,988/-  which is 9.62% above  the estimated cost of Rs. 2,70,64,110/- against justified rate of  11.48% above the estimated cost which workout to 1.66% below the justified rate. Permission be also accorded to take further action in anticipation of confirmation of minutes by the Council.

15. 	Draft Resolution:-

Resolved by the Council that the work may be awarded to lowest tenderer M/s Bhasin  Construction  at their tendered amount of Rs.2,96,68,988/- which is 9.62% above the estimated cost of Rs.2,70,64,110/- and the  department  may  initiate action in anticipation of confirmation of the minutes by the Council.

COUNCIL’S DECISION

Resolved by the Council to award the work to lowest tenderer M/s Bhasin  Construction  at their tendered amount of Rs.2,96,68,988/-, which is 9.62% above the estimated cost of Rs.2,70,64,110/-.

It was also resolved that further action in the matter be taken in anticipation of confirmation of the minutes by the Council.